## SPECS - Construction Phase
ENVIRONMENTAL SPECIFICATIONS COMPLIANCE MATRIX
|  | Contractor: | Murray Logan Construction, Inc.
|  | Project Name : | Trash Rake and Rack Replacement at S-319, Palm Beach County, Florida |  | Note: This form is used by the Corps to track compliance.
|  | Contract Number : |  |  | The form is provided to the contractor as a convenience
|  | Commencement Date : |  | Contingent upon Preconstruction Submittal Requirements | It does not supersede contract specifications or permit
|  | Expected Completion : |  |  | requirements.
| UPDATED LAST: | 2013-10-03
Day relative to Award | Specs Reference | Item Description | Deadline | Responsible Entity | First Submittal Recipient | Forwarded to: | STATUS
| 01 35 26 1.5.3.1 | Preconstruction conference | At least 14 days advance notice | COR/Construction Contractor |  | Attendees
30 | 01 57 20 1.4 | NPDES Construction Activities, Stormwater Permit | Permit required prior to construction activity. Application made to FDEP at least 48 hours in advance | Construction Contractor | FDEP, NPDES Construction Activities Permit Office | COR, SFWMD
20 | 01 57 20 1.5 | Env. Protection Plan | Within 20 days of NOA | Construction Contractor | COR | Corps PD-EQ/ES, SFWMD
20 | 01 57 20 1.5 | Bird, Eastern Indigo, Monitoring Qualifications | Within 20 days of NOA | Construction Contractor | COR | Corps PD-ES, SFWMD
| 01 57 20 1.5 | Biological Monitoring Closeout submittals | Within 30 days following completion of the project | Construction Contractor | COR | Corps PD-ES, SFWMD
TBD | 01 57 20 3.1.5.2 | Biological Monitoring Report | Within 60 days of completion of site clearing | Construction Contractor | COR, USFWS Field Office, Florid Fish and Wildlife | Corps PD-ES, SFWMD
N/A | 01 57 25 3.2.2 | Turbidity Testing and Reporting | Within 7 days after completion of each test. Submit for periods when Turbidity sampling is necessary | Construction Contractor | COR, PD-EQ, Lassiter | FDEP, SFWMD
Contact List |  |  |  | CESAJ PD-E (Branch Chief)--Eric Summa; (904) 232-1665; eric.p.summa@usace.army.mil
Contractor (Primary)-- Murray Logan Construction, Inc. |  |  |  | USFWS Vero Beach--Steve Mortellaro; (772) 562-3909; Steve_Mortellaro@fws.gov
CESAJ CD-GS (USACE COR)--John Hughes (561) 324-5182; john.j.hughes@usace.army.mil |  |  |  | FDEP Tallahassee, Kelli Edson - kelli.edson@dep.state.fl.us (850) - 245 -3180
CESAJ CD-WW (Resident Area Engineer)--Doug Wood, P.E. (561) 340-1520, cell 904-629-0049; walter.d.wood@usace.army.mil |  |  |  | SFWMD (Permitting and Compliance) - Holly Andreotta, handreot@sfwmd.gov (561) 242-5520 x3726 Cell: (561) 722-1340
CESAJ CD-W (South Florida Area Engineer)--George Cooper, P.E. (561) 626-5299; john.g.cooper@usace.army.mil |  |  |  | FDEP Compliance Officer, RPPS_COMP@DEP.state.fl.us
CESAJ PD-EQ (WQC, Turbidity Reports)--J. Aaron Lassiter; (904) 232-2708 james.a.lassiter@usace.army.mil |  |  |  | Refuge Project Manager - Rolf Olson, Deputy Manager, W: (561)735-6022, Cell: (561) 436-7632, rolf_olson@fws.gov
CESAJ PD-ES (NEPA, Wildlife Biologist)--Stacie Auvenshine; (904) 232-3694 stacie.j.auvenshine@usace.army.mil |  |  |  | FDEP Compliance Manager, Marissa Krueger Marissa.Krueger@dep.state.fl.us , (561) 682-2667

## SUP Permit
SPECIAL USE PERMIT COMPLIANCE MATRIX
|  | Project Name : | C-51 Stormwater Treatment Area - Trash Rake and Rack Replacement at S-319
|  | Permit Number : | SUP#41560-(B)11-020
|  | Contractor: | TBD |  |  | Note: This form is used by the Corps to track compliance. The form is
|  | Permit Commencement Date : |  |  |  | provided as a convenience and does not supersede contract specifications
|  | Permit Expiration Date : |  |  |  | or permit requirements.
| UPDATED LAST: | 2011-07-08
Day relative to Construction | Special Condition Reference | Item Description | Deadline |  | Responsible Entity | Forward to | STATUS
1 - 3 | 4 | Permittee must notify Refuge headquarters at least 24 hrs in advance when work will commence or when there will be a deviation in reported work schedule. Night time work requires 72 hrs advance notice | A minimum of 24 to 72 hrs in advance |  | Permittee | Refuge PM
N/A | 5 | All vehicles must be operated at less than 25 MPH |  |  | All parties on Refuge
N/A | 6 | Accidents or chemical spills that occur on the Refuge must be reported to Refuge Law Enforcement by calling 1-800-307-5789 | Immediately (if needed) |  | Permittee | 24-hr emergency number/ Refuge PM
N/A | 7 | All activities shall be coordinated with Refuge Project Manager | As needed |  | Permittee and Sub-Permittees | Refuge PM
N/A | 8 | A copy of the SUP must be kept on site and all personnel should be informed as to permit requirements while engaging in activities authorized within the SUP | N/A |  | Permittee and Sub-Permittees
N/A | 9 | Permittee must inform the Refuge regarding equipment/supplies/chemicals that will be brought onto the Refuge; be responsible for safe storage, transport, and removal of all materials brought onto the Refuge; all materials and equipment must be removed from site at end of project. | As needed |  | Permittee | Refuge PM
N/A | 10 | Permittee is allowed access only to the work site at STA1E and is not authorized to be on the L-40 south of STA1E or any other road on the Refuge |  |  | Permittee | Refuge PM
N/A | 11 | Permittee is not authorized to take alligators on the Refuge without prior approval. Permittee will notify the Refuge, after the fact, of the number, size and date of capture of all alligators taken within the STA1E construction area. | As needed |  | Permittee | Refuge PM
Refuge Contact List: |  |  |  | Contractor (Primary)-- TBD
Refuge Project Manager - Rolf Olson, Deputy Manager, W: (561)735-6022, Cell: (561) 436-7632, rolf_olson@fws.gov |  |  |  | CESAJ CD-WW (Resident Area Engineer)--Doug Wood, P.E. (561) 340-1520, cell 904-629-0049; walter.d.wood@usace.army.mil
Alternate Refuge Project Manager - Matt Harwell, Sr. Ecologist; W: (772)562-3909 ext 255, Cell: (561)755-3819; matthew_harwell@fws.gov |  |  |  | CESAJ CD-GS (USACE COR)--John Hughes (561) 324-5182; john.j.hughes@usace.army.mil
Law Enforcement - William Calvert, Supervisory LEO; W: (561)735-6033, Cell: (561)248-9014; william_calvert@fws.gov |  |  |  | CESAJ CD-W (South Florida Area Engineer)--George Cooper, P.E. (561) 626-5299; john.g.cooper@usace.army.mil
24-hr Emergency Number; 1-800-307-5789 |  |  |  | CESAJ PD-EQ (WQC, Turbidity Reports)--Aaron Lassiter; (904) 232-3642 james.a.lassiter@usace.army.mil
Additional Contact, Sylvia Pelizza, Refuge Manager - W: (561)735-6021, Cell: (561) 374-2734; sylvia_pelizza@fws.gov |  |  |  | CESAJ PD-ES (NEPA, Wildlife Biologist)--Stacie Auvenshine; (904) 232-3694 stacie.j.auvenshine@usace.army.mil