**VENICE BEACH NOURISHMENT, SARASOTA COUNTY, GROUP4-10-R-J0nn**

**WQC NO. 021217-005-JC Issued 6/13/2014 and Expires 6/13/2029 Prepared by Paul Karch 08/2014**

**ENVIRONMENTAL MATRIX**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TASK** | **REQUIREMENTS TO BE ACCOMPLISHED** | **TIMEFRAME** | **PERSON/TO TAKE ACTION** | **COMMENTS** |
| WQC |  |  |  |  |
|  |  |  |  |  |
|  | **PRE-CONSTRUCTION** |  |  |  |
|  |  |  |  |  |
| GC  10 | Send notice of commencement to DEP | At least 48 hours prior to construction | Corps CD | Send DEP anticipated start date and completion date. |
| SC  3 a. | Public Easement, NTP | At least 30 days prior to construction | Corps PD-EQ | Paul Karch submitted the Public Easement to DEP 8/25/14 |
| SC  3 b. | Construction Schedule and type of Dredge | At least 30 days prior to construction | Corps CD | Will be provided at the pre-con. |
| SC 3c. | Final Biological Opinion | At least 30 days prior to construction | Dredging Contractor will submit to Corps CD within 30 days of the pre-construction survey | Final Biological Plan needs to be approved by DEP prior to Construction |
| SC 3d. | Turbidity and Biological Monitoring POC | At least 30 days prior to construction | Dredging Contractor will submit to Corps CD and Corps CD will submit to DEP |  |
| SC 3f. | SOW Turbidity Monitoring | At least 30 days prior to construction | Dredging Contractor will submit to Corps CD and Corps CD will submit to DEP |  |
| SC  4 & 13 | Provide DEP, FWC, FWS, & permitted sea turtle surveyor written notification of the pre-construction conference | 21 days prior to the conference | Corps CD |  |

**VENICE BEACH NOURISHMENT, SARASOTA COUNTY, GROUP4-10-R-J020**

**WQC NO. 021217-005-JC Issued 6/13/2014 and Expires 6/13/2029 Prepared by Paul Karch 08/2014**

**ENVIRONMENTAL MATRIX**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TASK** | **REQUIREMENTS TO BE ACCOMPLISHED** | **TIMEFRAME** | **PERSON/TO TAKE ACTION** | **COMMENTS** |
| WQC |  |  |  |  |
|  | **PRE-CONSTRUCTION** |  |  |  |
|  |  |  |  |  |
| SC 33 | Pre-Construction Hardbottom Survey (Borrow Site) | 60 days after completion of survey | Dredging Contractor will submit to Corps CD and Corps CD will submit to DEP |  |
| SC 33 | Final Biological Plan | 60 days after completion of survey | Dredging Contractor will submit to Corps CD and Corps CD will submit to DEP |  |
| SC 14 | Shorebird Monitoring Qualifications | 20 days after award or 5 days after NTP | Dredging Contractor will submit to Corps CD and Corps CD will submit to DEP |  |
| SC 34 | Pipeline Corridors Pre-Construction Survey | 60 days after completion of survey | Dredging Contractor will submit to Corps CD and Corps CD will submit to DEP |  |
| SC  11 d. | Hopper Dredge Notification | Start-Up and Completion of Construction | Corps CD | Contact Allen.Foley@myfwc.com |
| Submit P&S | Submit P&S |  | PD-EQ |  |
|  | **DURING CONSTRUCTION** |  |  |  |
|  |  |  |  |  |
| GC 2&3 | Notify DEP of any deviations or noncompliance | If needed | Corps CD/Corps PD-EQ | The field office will notify PD-EQ and PD-EQ will notify DEP |

**VENICE BEACH NOURISHMENT, SARASOTA COUNTY, GROUP4-10-R-J020**

**WQC NO. 021217-005-JC Issued 6/13/2014 and Expires 6/13/2029 Prepared by Paul Karch 08/2014**

**ENVIRONMENTAL MATRIX**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TASK** | **REQUIREMENTS TO BE ACCOMPLISHED** | **TIMEFRAME** | **PERSON/TO TAKE ACTION** | **COMMENTS** |
| WQC |  |  |  |  |
|  |  |  |  |  |
|  | **DURING CONSTRUCTION** |  |  |  |
|  |  |  |  |  |
| GC  8 | Contractor to review DEP permit. Copy of permit kept at work site. | Prior to commencement of construction. | Contractor |  |
| GC  11 | Report finds of archeological artifacts to DEP and SHPO | If needed | Contractor/Corps CD/ Corps PD-E | Corps PD-E will notify DEP and SHPO |
| SC  10 | Manatee, Marine Turtle and Shorebird Protection | During Construction | Contractor |  |
| SC 11 | Hopper Dredging Conditions | During Construction | Contractor |  |
| SC 12 | Beach Maintenance | During Construction | Contractor |  |
| SC  14, 15 &16 | Shorebird Monitoring | Feb 15 to Sept 1 | Contractor |  |
| SC  17 | Marine Turtle Nest Surveys and Relocation | April 15 to October 31 | Contractor |  |
| SC  23 | Tilling Requirements | Prior to marine turtle nesting season | Contractor |  |
| SC  24 | Escarpment Surveys | Weekly and After Construction | Contractor |  |
| SC  29&30 | Submit water quality monitoring reports. | During Construction | Contractor | Submit the reports to Corps CD and PD-EQ and DEP on a weekly basis within seven days of collection. |

**VENICE BEACH NOURISHMENT, SARASOTA COUNTY, GROUP4-10-R-J020**

**WQC NO. 021217-005-JC Issued 6/13/2014 and Expires 6/13/2029 Prepared by Paul Karch 08/2014**

**ENVIRONMENTAL MATRIX**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TASK** | **REQUIREMENTS TO BE ACCOMPLISHED** | **TIMEFRAME** | **PERSON/TO TAKE ACTION** | **COMMENTS** |
| WQC |  |  |  |  |
|  |  |  |  |  |
|  | **DURING CONSTRUCTION** |  |  |  |
|  |  |  |  |  |
| SC 33. | Borrow Area Sedimentation Monitoring | During Construction | Contractor |  |
| SC 34 | Pipeline Corridor Monitoring | During Construction | Contractor |  |
|  | **POST CONSTRUCTION** |  |  |  |
| GC  12 | Send notice of completion to DEP | Within 60 days after construction is completed | Corps CD |  |
| SC  28 | Artificial Light Surveys | Between (May 1 and May 15) and (July 15 and August 1) | City of Venice |  |
| SC 9 | Post-Construction Sediment Testing Results | Within 90 days following beach placement | Corps EN-GG will take the samples, submit to DEP |  |
| SC 23 | Tilling Requirements | Annual for 3 years if failed compact sampling | City of Venice |  |
| SC  24 | Escarpment Surveys | Annual for 3 years | City of Venice |  |
| SC  35 | Topographic/Bathymetric | Within 60 days completion of project Beach and Borrow Sites | Corps |  |
| SC  35 | Topographic/Bathymetric | Annually for 3 years | TBD |  |
| P3BO  6/22/13 | Piping Plover Surveys | Within 30 days of completion of construction | Contractor submit to COR, PD-E, USFWS, and FWC |  |

POC

FDEP Bureau of Beaches and Coastal Systems

Bob Martinez Building

2600 Blair Stone Road – MS3566

Tallahassee, Florida 32399

Fax: (850) 4885257

DEP Southwest District Office

Submerged Lands & Environmental Resources

13051 N. Telecom Parkway Temple Terrace, Florida 33637

phone: 813-632-7600, fax: 813-632-7665

Imperiled Species Management Section

Florida Fish & Wildlife Conservation Commission

620 South Meridian Street

Tallahassee, Florida 32399-1600

PHONE: (850) 922-4330, Fax: (850) 921-4369

Southwest Region

Ms. Nancy Douglass

FL Fish and Wildlife Conservation Commission

3900 Drane Field Road

Lakeland, FL 33811-1299

(863) 648-3205

Telephone #s:

Contractor TBA

FDEP BBCS (Compliance Officer): Charlotte Hand; 850-414-7716; [JCPCompliance@dep.state.fl.us](mailto:JCPCompliance@dep.state.fl.us)

CESAJ-PD-EQ (Water Quality): Paul Karch; 904-232-2168; [paul.j.karch@usace.army.mil](mailto:paul.j.karch@usace.army.mil)

CESAJ-PD-EC (Biologist): Aubree Hershorin; 904-232-2136; [Aubree.G.Hershorin@usace.army.mil](mailto:Aubree.G.Hershorin@usace.army.mil)

CESAJ-PM-WN (Project Management): Millan Mora: 904-232-1454; [Millan.A.Mora@usace.army.mil](mailto:Millan.A.Mora@usace.army.mil)

CESAJ-CD-GS (COR): Erin Duffy; 863-471-1741; [Erin.M.Duffy@usace.army.mil](mailto:Erin.M.Duffy@usace.army.mil)